## Maintenance Log for Website 202
Florida Architecture Maintenance Log
# | Date | Architecture | Source | Contact | CR Form | Change | Disposition | Recommend Update | Update Target | Incorporated | Incorporation Date | Status / Notes
202 | 2025-03-12 | D4/6 RITSA | Change Request | Nick Slupecki / FDOT District 4 | Y | New Project - New District 4 Regional Transportation Management Center (RTMC); New element - FDOT District 4 RTMC (may replace, modify or duplicate the current Broward County TMC element); Roles and responsibilities - the current roles and responsibilities of Broward County TMC will change to differentiate from the new RTMC; New Architecture flows - between Broward County TMC and the new District 4 RTMC. The current FDOT District 4 RTMC is co-located with the Broward County TMC in a Broward County owned building, and referenced as Broward County TMC in the current RITSA. District 4 is planning to design and construct a new RTMC. The anticipated new RTMC will be located next to the District 4 headquarters, and physically separated from the Broward County TMC network. Additionally, new connectivity between the two facilities will be established. Therefore, it will be a major update to the current RITSA. More details will be provided as the project proceeds to the design phase. | This project is currently being scoped and no specific information has been provided. It is recommended to hold any architecture update until the project scope has been defined. | Yes |  |  |  | Pending project scope before architecture update activities are advanced.
204 | 2025-07-21 | SITSA | Change Request | Christine McDonald / FDOT CO OT | Y | Stakeholder Name Change - Civil Integrated Management (CIM) is now known as the Office of Operational Technology (OOT). I am requesting that all previous references to CIM on the Florida Statewide and Regional ITS Architectures website be changed to OOT. | SITSA Stakeholder Name change to be made; check RITSAs for CIM reference and revise as appropriate. | Yes | 2025 | Yes | 5/21/26
205 | 2025-09-08 | SITSA | Change Request | JoAnna Hand / FDOT CO | Y | Rename: V2X DEP has been renamed to Data Exchange for Operational Technlogy (DEPOT). | SITSA Element Name change to me; check RITSAs/FTE for V2X DEP reference and revise as appropriate. | Yes | 2026 | Yes | 5/21/26 | Carla confirmed it should be 'Operational' vs 'Operations'.
206 | 2025-12-04 | D4/6 RITSA | Change Request | Sergio Bravo / FDOT D6 | Y | Project status change: Incident Response Vehicle Pilot - The FDOT District 6 Incident Response Vehicle Pilot Project has been fully deployed and is now operational. Final implementation activities have been completed, and the pilot is no longer in the “Planned” phase. The project status should be changed from “Planned” to “Existing”. | D6 project status to be changed; will evalute status changes for elements, flows, etc in the project. | Yes | 2026 | Yes | 1/14/26
207 | 2025-12-04 | D4/6 RITSA | Change Request | Sergio Bravo / FDOT D6 | Y | Project status change: Traffic Signal System Upgrade Monroe County - The D6 TSM&O Office has fully commenced operations and maintenance for traffic signals in the City of Key West (17 signals, 5 HAWKs) along US 1. Infrastructure was upgraded with new controllers, wireless routers, and remote management software for the SunGuide TMC. Status Update: Planned to Existing. | D6 project status to be changed; will evalute status changes for elements, flows, etc in the project. | Yes | 2026 | Yes | 1/14/26
208 | 2025-12-04 | D4/6 RITSA | Change Request | Sergio Bravo / FDOT D6 | Y | Project status change: Warning Gate System Status Notification - The FDOT District 6 Warning Gate System Status Notification project has been implemented and is currently operational. This system now provides real-time status of warning gates for the 95 Express system. The status should be changed from “Planned” to “Existing.” All associated service packages (roadway closure management, traveler information), interconnects, and information flows should be updated from “Planned” to “Existing.” | D6 project status to be changed; will evalute status changes for elements, flows, etc in the project. | Yes | 2026 | Yes | 1/14/26
209 | 2025-12-05 | D5 RITSA | Change Request | Eric Hill / MetroPlan Orlando | Y | 2050 MTP and MetroPlan Orlando TSM&O Master Plan link updates: MetroPlan Orlando is finalizing its LRTP, the 2050 Metropolitan Transportation Plan (MTP). It will be approved by the Board on December 10, 2025. The final document will be available here: https://metroplanorlando.gov/plans/2050-metropolitan-transportation-plan/ The MetroPlan Orlando TSM&O Master Plan (2024) is also available here: https://metroplanorlando.gov/plans/transportation-systems-management-operations-master-plan/ | Update the Resources page with the link provided in the CR form | Yes | 2026 | Yes | 1/9/26
210 | 2025-12-05 | D5 RITSA | Change Request | Stephan Harris / Volusia-Flagler TPO | Y | Volusia-Flagler TPO 2050 LRTP link update: The Volusia-Flagler TPO adopted the Volusia-Flagler 2050 LRTP on September 17, 2025. The final document is available here: https://www.r2ctpo.org/planning-studies/volusia-flagler-2050-long-range-transportation-plan/ | Update the Resources page with the link provided in the CR form | Yes | 2026 | Yes | 1/9/26
211 | 2025-12-05 | D5 RITSA | Change Request | Sarah Kraum / Space Coast TPO | Y | Space Coast TPO LRTP and ITS Master Plan (2021) link updates: Space Coast TPO is finalizing its LRTP, the Advance 2050 LRTP. It was adopted by the Board in September 2025. The final document will be available here shortly: https://www.spacecoasttpo.com/what-we-do/planning/core-work-products/long-range-transportation-plan The SCTPO ITS Master Plan (2021) is also available here: https://www.spacecoasttpo.com/what-we-do/planning/intelligent-transportation-system-its-master-plan | Update the Resources page with the link provided in the CR form | Yes | 2026 | Yes | 1/9/26
212 | 2025-12-05 | D5 RITSA | Change Request | Rob Balmes / Ocala Marion TPO | Y | Ocala Marion TPO LRTP link update: The Ocala Marion TPO adopted its LRTP, Navigating the Future 2050 LRTP, on November 13, 2025. The final document is available here: https://storymaps.arcgis.com/stories/c88b20f1d8e74c5f96dd7fdc9f98a5c3 | Update the Resources page with the link provided in the CR form | Yes | 2026 | Yes | 1/9/26
213 | 2025-12-05 | D5 RITSA | Change Request | Michael Woods / Lake-Sumter MPO | Y | Lake-Sumter MPO 2050 LRTP link update: Lake-Sumter MPO is finalizing its 2050 Long Range Transportation Plan. The Board is expected to approve the LRTP in late 2025. The final document will be available here shortly: https://www.lakesumtermpo.com/planning-documents/2050-lrtp/ | Update the Resources page with the link provided in the CR form | Yes | 2026 | Yes | 1/9/26
214 | 2025-12-15 | D1 RITSA | Change Request | Nikesh Patel / City of Sarasota | Y | Project Status Change - City of Sarasota Smart School Zone Project | D1 project status to be changed; will evaluate status changes for elements, flows, etc. in the project | Yes | 2026 | Yes | 1/16/26
215 | 2026-01-22 | D4/6 RITSA | Change Request | Sergio Bravo / FDOT D6 | Y | Project List and Completed Projects: The status of 3 District 6 projects was updated as requested. However, we noted that these three projects remain listed under the “Projects” tab. Based on the Projects page description, which indicates that the tab is intended to display ongoing, planned, and future projects, we believe the completed and existing District 6 projects may need to be unlisted. | Mark projects definitively as "complete" and explain in page description | Yes | 2026 | Yes | 2/19/26
216 | 2026-01-09 | D5 RITSA | Email | David Williams / FDOT D5 | Y | The 2045 LRTP was superseded by the Volusia-Flagler TPO 2050 LRTP. River-to-Sea TPO changed its name to Volusia-Flagler TPO in late 2024. | Update the Resources page with the link to the new plan; change the stakeholder name from R2CTPO to VFTPO and update other affected elements. | Yes | 2026 | Yes | 2/19/26 | Came in response to request to review D5 updates; as an Oh-by-the-way, this happened too sort of thing.
| Architecture | Log Items | 2025-2027 Update Recommended | 2025-2027 Targets Incorporated | Change Forms | Comments | Maintenance Log Status | Total Incorp | N/A Log Items | Change Forms Remain | Items Remain | Comments
| SITSA | 2 | 2 | 2 | 2 |  | SITSA | 2 | 0 | 0 | 0
| D1 RITSA | 1 | 1 | 1 | 1 |  | D1 RITSA | 1 | 0 | 0 | 0
| D2 RITSA | 0 | 0 | 0 | 0 |  | D2 RITSA | 0 | 0 | 0 | 0
| D3 RITSA | 0 | 0 | 0 | 0 |  | D3 RITSA | 0 | 0 | 0 | 0
| D4/6 RITSA | 5 | 5 | 4 | 5 |  | D4/6 RITSA | 4 | 0 | 1 | 0
| D5 RITSA | 6 | 6 | 6 | 6 |  | D5 RITSA | 6 | 0 | 0 | 0
| D7 RITSA | 0 | 0 | 0 | 0 |  | D7 RITSA | 0 | 0 | 0 | 0
| FTE RITSA | 0 | 0 | 0 | 0 |  | FTE RITSA | 0 | 0 | 0 | 0
| All Architectures | 0 | 0 | 0 | 0 |  | All Architectures | 0 | 0 | 0 | 0
| Total | 14 | 14 | 13 | 14 |  |  | 13 | 0 | 1 | 0